## Sheet1
DATE | KEY DISCUSSION POINTS | BLOCKERS
2018-01-06 | Everyone had ideas on their datasets and some sense of what they would try to present. | Everyone lacked a sense of what the project should entail. Committed to follow up with Dhrumil next week
2018-01-09 | Face-to-face meeting held. Everyone had completed their part of the MVP with few issues. Discussion on what we needed to include and the process for pull requests and branching. | Simon had a question on how to integrate images into html. Followed up with Ihsaan
2018-01-10 | Face-to-face meeting held. Designed common layout for webpages and everyone making progress on their respective sections. | No blockers
2018-01-11 | In-class meeting. Refined user stories and agreed integration of Alex's menu bar. | Queries on how we should allocate work appropriately through the bingo process. Clarified with Dhurmil.
2018-01-12 | Face-to-face meeting. Everyone had achieved a working model and discussion focussed on ensuring that the formatting was consistent between the pages | Technical issues on how to integrate Alex's menu bar.